## Work Items
Key | Type | Epic | Parent | Work item | Assignee | Status | Start | Due | Resolved | Notes
KAN-91 | Epic | Meetings |  | Meetings | Indiana Silbert | Done | 28/08/2026 | 09/10/2026 | 09/10/2026 | Members required to be present: @Shakiba B @Sangjun Nam @Banyei Chan @Lincoln van Halen @Indiana Silbert
KAN-102 | Task | Meetings |  | Meetup on 28th in Library | Indiana Silbert | Done | 28/09/2026 | 28/09/2026 | 28/09/2026 | During Tuition-free week everyone attend: @Shakiba B @Sangjun Nam @Banyei Chan @Lincoln van Halen @Indiana Silbert
KAN-104 | Task | Meetings |  | Minutes | Indiana Silbert | Done |  | 09/10/2026 | 09/10/2026 | @Indiana Silbert , please upload minutes to Google Doc after each meeting, thanks * 28/08 * 04/09 * 11/09 * 18/09 * 25/09 * 28/09 * 02/10 * 09/10
KAN-135 | Task | Meetings |  | Project Management | Sangjun Nam | Done |  | 09/10/2026 | 09/10/2026
KAN-103 | Subtask | Meetings | Meetup on 28th in Library | Library Room Booking | Indiana Silbert | Done |  |  | 28/09/2026 | Need booking from 12-6 pm * 12-2 pm: @Indiana Silbert * 2-4 pm: @Sangjun Nam * 4-6 pm: @Lincoln van Halen
KAN-136 | Subtask | Meetings | Project Management | Effort estimation (estimated hours) | Shakiba B | Done |  |  | 09/10/2026
KAN-137 | Subtask | Meetings | Project Management | Gantt chart | Shakiba B | Done |  |  | 09/10/2026
KAN-138 | Subtask | Meetings | Project Management | WBS | Shakiba B | Done |  |  | 09/10/2026
KAN-140 | Subtask | Meetings | Project Management | Weekly progress check or status update | Indiana Silbert | Done |  |  | 09/10/2026
KAN-76 | Epic | Application Setups |  | Application Setups | Lincoln van Halen | Done | 31/08/2026 | 07/10/2026 | 09/10/2026
KAN-80 | Task | Application Setups |  | GitHub | Shakiba B | Done |  | 04/09/2026 | 09/10/2026 | Target date: 04/09
KAN-81 | Task | Application Setups |  | Jira | Lincoln van Halen | Done |  | 04/09/2026 | 09/10/2026 | Target date: 04/09
KAN-82 | Task | Application Setups |  | Wazuh | Lincoln van Halen | Done |  | 02/10/2026 | 09/10/2026 | Target date: 02/10
KAN-84 | Task | Application Setups |  | Google Docs | Indiana Silbert | Done |  | 04/09/2026 | 28/09/2026 | Target date: 04/09
KAN-87 | Task | Application Setups |  | Virtual Machines | Sangjun Nam | Done |  | 11/09/2026 | 28/09/2026
KAN-94 | Task | Application Setups |  | Malicious Websites | Sangjun Nam | Done |  | 02/10/2026 | 09/10/2026
KAN-100 | Task | Application Setups |  | Apache | Banyei Chan | Done |  | 11/09/2026 | 09/10/2026 | Target date: 11/09
KAN-83 | Subtask | Application Setups | GitHub | Add all members | Shakiba B | Done |  |  | 28/09/2026 | Target date: 11/09
KAN-86 | Subtask | Application Setups | GitHub | Upload CSRF Website | Banyei Chan | Done |  |  | 09/10/2026 | Target date: 28/09
KAN-88 | Subtask | Application Setups | Virtual Machines | For Path Traversal | Lincoln van Halen | Done |  |  | 28/09/2026 | Target date: 11/09
KAN-89 | Subtask | Application Setups | Virtual Machines | For CSRF (x2) | Banyei Chan | Done |  |  | 28/09/2026 | @Banyei Chan @Sangjun Nam 04/09
KAN-95 | Subtask | Application Setups | Malicious Websites | Path Traversal Web Servers | Lincoln van Halen | Done |  |  | 09/10/2026 | * HTTP/GET Request * Track using Wireshark
KAN-96 | Subtask | Application Setups | Malicious Websites | CSRF | Banyei Chan | Done |  |  | 09/10/2026 | * Anyone should be able to log in * Logged in user then visits a separate website with malicious Code * Authentication Session Token is passed from the two websites by the browser
KAN-113 | Subtask | Application Setups | Jira | Jira Organisation | Shakiba B | Done |  |  | 09/10/2026
KAN-42 | Epic | Research |  | Research | Banyei Chan | Done |  | 29/09/2026 | 09/10/2026
KAN-92 | Task | Research |  | CSRF | Banyei Chan | Done |  | 28/09/2026 | 09/10/2026 | @Shakiba B @Banyei Chan @Indiana Silbert
KAN-93 | Task | Research |  | Path Traversal | Indiana Silbert | Done |  | 29/09/2026 | 09/10/2026
KAN-97 | Subtask | Research | CSRF | Mitigation Strategies | Banyei Chan | Done |  |  | 09/10/2026 | Target date: 18/09
KAN-98 | Subtask | Research | CSRF | Vulnerability Exploitation | Banyei Chan | Done |  |  | 09/10/2026 | Due on the 18/09
KAN-99 | Subtask | Research | CSRF | Vulnerability Identification and Explanation | Banyei Chan | Done |  |  | 09/10/2026 | Due on the 04/09
KAN-105 | Subtask | Research | CSRF | Impact on Confidentiality, Availability, and Integrity | Shakiba B | Done |  |  | 09/10/2026 | Target date: 28/09
KAN-106 | Subtask | Research | Path Traversal | Impact on Confidentiality, Availability, and Integrity | Indiana Silbert | Done |  |  | 09/10/2026 | Target date: 11/09
KAN-107 | Subtask | Research | Path Traversal | Vulnerability Identification and Explanation | Indiana Silbert | Done |  |  | 09/10/2026 | Target date: 11/09
KAN-108 | Subtask | Research | Path Traversal | Vulnerability Exploitation | Indiana Silbert | Done |  |  | 09/10/2026 | Target date: 04/09
KAN-109 | Subtask | Research | Path Traversal | Mitigation Strategies | Indiana Silbert | Done |  |  | 09/10/2026 | Target date: 18/09
KAN-115 | Subtask | Research | CSRF | Why this vulnerability is common or significant (real-world examples, OWASP ranking) | Shakiba B | Done |  |  | 09/10/2026
KAN-116 | Subtask | Research | Path Traversal | Why this vulnerability is common or significant (real-world examples, OWASP ranking) | Lincoln van Halen | Done |  |  | 09/10/2026
KAN-117 | Subtask | Research | Path Traversal | Step-by-step explanation of the exploit | Lincoln van Halen | Done |  |  | 09/10/2026
KAN-118 | Subtask | Research | CSRF | Step-by-step explanation of the exploit | Sangjun Nam | Done |  |  | 09/10/2026
KAN-131 | Epic | Development |  | Development | Sangjun Nam | To Do
KAN-119 | Task | Development |  | CSRF | Sangjun Nam | To Do
KAN-125 | Task | Development |  | Path Traversal | Lincoln van Halen | To Do
KAN-120 | Subtask | Development | CSRF | Write the vulnerable code | Banyei Chan | To Do
KAN-122 | Subtask | Development | CSRF | Write the exploit script or payload | Banyei Chan | To Do
KAN-123 | Subtask | Development | CSRF | Implement the mitigated code (anti-CSRF tokens and SameSite cookies) | Sangjun Nam | To Do
KAN-124 | Subtask | Development | CSRF | Push to GitHub through a pull request | Sangjun Nam | To Do
KAN-126 | Subtask | Development | Path Traversal | Write the vulnerable code | Indiana Silbert | To Do
KAN-128 | Subtask | Development | Path Traversal | Write the exploit script or payload | Indiana Silbert | To Do
KAN-129 | Subtask | Development | Path Traversal | Implement the mitigated code (path canonicalisation and an allowlist) | Lincoln van Halen | To Do
KAN-130 | Subtask | Development | Path Traversal | Push to GitHub through a pull request | Lincoln van Halen | To Do
KAN-132 | Epic | Detection and Tracing |  | Detection and Tracing | Shakiba B | To Do
KAN-143 | Task | Detection and Tracing |  | Capture the attack in Burp Suite or OWASP ZAP | Banyei Chan | To Do
KAN-144 | Task | Detection and Tracing |  | Collect Apache access/ error logs showing the attack | Lincoln van Halen | To Do
KAN-145 | Task | Detection and Tracing |  | Configure Wazuh rules or alerts for the attack | Lincoln van Halen | To Do
KAN-146 | Task | Detection and Tracing |  | Capture Path Traversal requests in Wireshark | Banyei Chan | To Do
KAN-147 | Task | Detection and Tracing |  | Link each piece of evidence to an attack step, for the report | Sangjun Nam | To Do
KAN-133 | Epic | Testing and QA |  | Testing and QA | Shakiba B | To Do
KAN-148 | Task | Testing and QA |  | Peer code review of the vulnerable and mitigated code | Shakiba B | Done |  |  | 09/10/2026
KAN-149 | Task | Testing and QA |  | Second member reproduces each exploit in a clean VM | Shakiba B | Done |  |  | 09/10/2026
KAN-150 | Task | Testing and QA |  | Re-run each exploit against the mitigated code and confirm it fails | Shakiba B | Done |  |  | 09/10/2026
KAN-151 | Task | Testing and QA |  | Check that the tracing evidence matches the attack steps | Shakiba B | Done |  |  | 09/10/2026
KAN-152 | Task | Testing and QA |  | Proofread the final report and check references | Banyei Chan | To Do
KAN-39 | Epic | Report |  | Report | Indiana Silbert | In Progress | 31/08/2026 | 09/10/2026
KAN-77 | Task | Report |  | CSRF | Sangjun Nam | In Progress |  | 09/10/2026
KAN-78 | Task | Report |  | Path Traversal | Lincoln van Halen | In Progress |  | 09/10/2026
KAN-79 | Task | Report |  | General Structure | Sangjun Nam | Done |  | 18/09/2026 | 09/10/2026
KAN-112 | Task | Report |  | Group Sheet | Indiana Silbert | Done |  | 04/09/2026 | 28/09/2026 | Target date: 04/09
KAN-154 | Task | Report |  | Team organisation and project plan | Shakiba B | In Progress |  | 09/10/2026
KAN-156 | Task | Report |  | Mitigation strategies and security recommendations | Indiana Silbert | In Progress |  | 09/10/2026
KAN-157 | Task | Report |  | Conclusion | Lincoln van Halen | In Progress |  | 09/10/2026
KAN-158 | Task | Report |  | References (IEEE or APA) | Banyei Chan | In Progress |  | 09/10/2026
KAN-159 | Task | Report |  | Appendices (code listings, full meeting minutes) | Shakiba B | In Progress |  | 09/10/2026
KAN-160 | Task | Report |  | Package and submit: code zip with a README, report PDF | Sangjun Nam | In Progress |  | 09/10/2026
KAN-90 | Subtask | Report | General Structure | Formatting | Sangjun Nam | Done |  |  | 09/10/2026 | Target date: 04/09
KAN-101 | Subtask | Report | General Structure | Organise Research | Lincoln van Halen | Done |  |  | 09/10/2026
KAN-50 | Epic | Presentation |  | Presentation | Indiana Silbert | Planned | 31/08/2026 | 19/10/2026
KAN-110 | Task | Presentation |  | Slides | Indiana Silbert | Planned |  | 16/10/2026
KAN-111 | Task | Presentation |  | Presentation Booking | Indiana Silbert | Done |  | 10/09/2026 | 28/09/2026
KAN-161 | Task | Presentation |  | Demo script and run order | Lincoln van Halen | Planned |  | 16/10/2026
KAN-162 | Task | Presentation |  | Set up the demo environment on the presentation machine | Shakiba B | Planned |  | 16/10/2026
KAN-163 | Task | Presentation |  | Backup screen recording of the demo, in case the live demo breaks | Shakiba B | Planned |  | 16/10/2026
KAN-164 | Task | Presentation |  | Group rehearsal | Indiana Silbert | Planned |  | 16/10/2026
KAN-165 | Task | Presentation |  | Split speaking parts | Shakiba B | Planned |  | 16/10/2026

## Summary
Jira work items by epic and status
Counts tasks and subtasks (epics excluded). Calculated from the Work Items sheet.
Epic | To Do | Planned | In Progress | Done | Total | % Done
Meetings | 0 | 0 | 0 | 8 | 8 | 100%
Application Setups | 0 | 0 | 0 | 14 | 14 | 100%
Research | 0 | 0 | 0 | 14 | 14 | 100%
Development | 10 | 0 | 0 | 0 | 10 | 0%
Detection and Tracing | 5 | 0 | 0 | 0 | 5 | 0%
Testing and QA | 1 | 0 | 0 | 4 | 5 | 80%
Report | 0 | 0 | 8 | 4 | 12 | 33.33%
Presentation | 0 | 6 | 0 | 1 | 7 | 14.29%
Total | 16 | 6 | 8 | 45 | 75 | 60%
Work items by assignee
Assignee | To Do | Planned | In Progress | Done | Total
Banyei Chan | 5 | 0 | 1 | 8 | 14
Indiana Silbert | 2 | 2 | 1 | 12 | 17
Lincoln van Halen | 5 | 1 | 2 | 7 | 15
Sangjun Nam | 4 | 0 | 2 | 6 | 12
Shakiba B | 0 | 3 | 2 | 12 | 17
Source: Jira CSV export, 09/10/2026. Excluded: work items created in error and labelled for deletion ("DEL"), and one duplicate Testing epic. Account IDs replaced with member names; dates shown as DD/MM/YYYY.